## Priority & Sequence
Seq # | Priority | Target Phase / Sprint | Processor ID | Step Processor Name | Family Code | Family Name | Current Status | Effort | Assigned Owner / Team | Target Release / Date | Key Dependencies & Tech Seam | Business Impact & Value
1 | P0 | Phase 1: Cloud & Lake | SP-ACQ-06 | AWS S3 object ingest | ACQ | Collectors & Ingestion | Planned | Med |  |  | AWS SDK v2, `inspecto-connectors` | Cloud file ingestion baseline; table stakes for AWS environments
2 | P0 | Phase 1: Cloud & Lake | SP-ACQ-07 | Azure Blob & ADLS Gen2 ingest | ACQ | Collectors & Ingestion | Partial | Low |  |  | Azure Blob SDK, directory recursion test | Quick win: verify ADLS Gen2 hierarchy on existing Azure connector
3 | P0 | Phase 1: Core Formats | SP-PRS-05 | XML / XPath / DOM unpacker | PRS | Extraction & Format Parsers | Partial | Med |  |  | StAX / VTD-XML, `parser.xml` node | Closes major enterprise ingestion gap beyond existing tree plugin
4 | P0 | Phase 1: Core Formats | SP-PRS-14 | Apache Avro binary decoder | PRS | Extraction & Format Parsers | Planned | Med |  |  | DuckDB Avro scanner / Apache Avro | High-speed ingestion for Kafka dumps and Hadoop migration feeds
5 | P0 | Phase 1: Core Formats | SP-ACQ-05 | Multi-sheet Excel workbook ingest | ACQ | Collectors & Ingestion | Partial | Low |  |  | Apache POI / DuckDB Excel metadata | Quick win: sheet discovery wrapper feeding existing `parser.xlsx`
6 | P0 | Phase 1: Advanced ETL | SP-XFM-07 | Dynamic pivot / transpose | XFM | Transformers & Dimensional Modeling | Planned | Low |  |  | DuckDB `PIVOT` syntax lowerer | Critical for financial, tabular, and time-matrix reporting
7 | P0 | Phase 1: Advanced ETL | SP-XFM-08 | Unpivot / column flattener | XFM | Transformers & Dimensional Modeling | Planned | Low |  |  | DuckDB `UNPIVOT` syntax lowerer | Normalizes wide survey/Excel tables into tidy relational rows
8 | P0 | Phase 1: Quality & Gov | SP-DQ-06 | Schema drift & new-field detector | DQ | Data Quality, Validation & Cleansing | Partial | Med |  |  | Schema comparator, drift event bridge | Prevents silent data corruption when upstream providers add fields
9 | P0 | Phase 1: Quality & Gov | SP-SNK-15 | Dead-letter queue (DLQ) | SNK | Sinks, Storage & Destinations | Planned | Med |  |  | DLQ store layout, error payload wrapper | Safe landing for poisoned records without failing batch jobs
10 | P1 | Phase 2: Streaming | SP-ACQ-09 | Apache Kafka consumer | ACQ | Collectors & Ingestion | Partial | Med |  |  | Kafka consumer group, file buffer | Connects event-driven Kafka topics into micro-batch pipelines
11 | P1 | Phase 2: Streaming | SP-SNK-11 | Apache Kafka topic producer | SNK | Sinks, Storage & Destinations | Planned | Med |  |  | Kafka Producer client, JSON/Avro encoder | Enables reverse-ETL streaming into downstream consumer buses
12 | P1 | Phase 2: Lakehouse | SP-ACQ-15 | Delta Lake table reader | ACQ | Collectors & Ingestion | Planned | High |  |  | `delta-kernel-java` / DuckDB Delta ext | Ingests versioned Delta tables directly from Databricks / S3
13 | P1 | Phase 2: Lakehouse | SP-SNK-07 | Delta Lake table sink | SNK | Sinks, Storage & Destinations | Planned | High |  |  | Delta Lake ACID transaction commit | Commits pipeline outputs directly into Lakehouse Delta tables
14 | P1 | Phase 2: Lakehouse | SP-ACQ-16 | Apache Iceberg table ingest | ACQ | Collectors & Ingestion | Planned | High |  |  | Iceberg Core client, catalog reader | Interoperability with Snowflake/Trino Iceberg storage
15 | P1 | Phase 2: Lakehouse | SP-SNK-08 | Apache Iceberg append/upsert sink | SNK | Sinks, Storage & Destinations | Planned | High |  |  | Iceberg manifest commit coordinator | Multi-engine lakehouse destination standard
16 | P1 | Phase 2: Modeling | SP-XFM-12 | Slowly changing dimension (SCD2) | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | Key anti-join, `valid_from`/`valid_to` | Essential dimensional warehouse history tracking
17 | P1 | Phase 2: Modeling | SP-XFM-09 | Rank & Top-N pruner | XFM | Transformers & Dimensional Modeling | Planned | Low |  |  | DuckDB `ROW_NUMBER() / QUALIFY` | High-utility row pruner for leaderboards and deduplication
18 | P1 | Phase 2: Modeling | SP-XFM-10 | Array / object exploder & flattener | XFM | Transformers & Dimensional Modeling | Planned | Low |  |  | DuckDB `UNNEST` lowerer | Flattens repeated JSON arrays into separate relation rows
19 | P1 | Phase 2: Modeling | SP-XFM-13 | Monotonic surrogate key generator | XFM | Transformers & Dimensional Modeling | Planned | Low |  |  | Watermark offset + sequence generator | Generates consistent primary integer keys for star schemas
20 | P1 | Phase 2: Enrichment | SP-ENR-03 | Redis in-memory cache lookup | ENR | Enrichment, Entity Resolution & AI/ML | Planned | Med |  |  | Lettuce / Jedis client, connection pool | Sub-millisecond reference lookup for IDs, sessions, user flags
21 | P1 | Phase 2: Enrichment | SP-ENR-04 | Dynamic microservice REST enricher | ENR | Enrichment, Entity Resolution & AI/ML | Planned | Med |  |  | Async HTTP client, token bucket rate | In-flight REST API enrichment for live external data lookups
22 | P1 | Phase 2: Security (Ent) | SP-DQ-12 | PII masking & tokenization | DQ | Data Quality, Validation & Cleansing | Planned | Med |  |  | Regex mask templates, FPE engine | Regulatory compliance (GDPR/HIPAA) for sensitive data masking
23 | P1 | Phase 2: Security (Ent) | SP-DQ-14 | GDPR / CCPA field redactor | DQ | Data Quality, Validation & Cleansing | Planned | Med |  |  | Subject key matching, NULL overwriter | Automated data subject right-to-be-forgotten erasure
24 | P1 | Phase 2: Integrations | SP-SNK-14 | Outbound webhook dispatcher | SNK | Sinks, Storage & Destinations | Partial | Low |  |  | Webhook POST executor, retry policy | Pushes event batches directly to third-party HTTP receivers
25 | P1 | Phase 2: Integrations | SP-SNK-13 | Email & report dispatcher | SNK | Sinks, Storage & Destinations | Partial | Low |  |  | Wire `mail.send` job to sink seam | Sends scheduled data extracts and reports via email
26 | P2 | Phase 3: Multi-Cloud | SP-ACQ-08 | Google Cloud Storage ingest | ACQ | Collectors & Ingestion | Planned | Med |  |  | Google Cloud Storage client SDK | Completes the tri-cloud storage ingest suite (AWS, Azure, GCP)
27 | P2 | Phase 3: Multi-Cloud | SP-ACQ-17 | Snowflake / BigQuery ingest | ACQ | Collectors & Ingestion | Planned | Med |  |  | Cloud warehouse JDBC / Arrow Flight | High-speed bulk read from enterprise cloud warehouses
28 | P2 | Phase 3: Connectors | SP-ACQ-18 | REST API poller & paged ingest | ACQ | Collectors & Ingestion | Planned | Med |  |  | HTTP pagination handler (cursor/page) | Pulls from SaaS REST endpoints (Salesforce, Stripe, Jira)
29 | P2 | Phase 3: Connectors | SP-ACQ-19 | HTTP webhook listener endpoint | ACQ | Collectors & Ingestion | Planned | Med |  |  | Inbound HTTP handler, HMAC validator | Real-time push ingestion for third-party webhook payloads
30 | P2 | Phase 3: Formats | SP-PRS-13 | Protocol Buffers decoder | PRS | Extraction & Format Parsers | Planned | Med |  |  | Dynamic Protobuf schema loader | High-efficiency binary serialization parsing
31 | P2 | Phase 3: Formats | SP-PRS-16 | Grok / Logstash expression matcher | PRS | Extraction & Format Parsers | Planned | Low |  |  | Java Grok library, regex compiler | Ingests unstructured infrastructure and application log lines
32 | P2 | Phase 3: Formats | SP-PRS-17 | Syslog RFC 5424 / RFC 3164 parser | PRS | Extraction & Format Parsers | Planned | Low |  |  | Syslog header tokenizer | Standardized network and Linux system log parsing
33 | P2 | Phase 3: Formats | SP-PRS-09 | Key-value / logfmt parser | PRS | Extraction & Format Parsers | Planned | Low |  |  | Logfmt scanner / tokenizer | Parses structured key-value log formats
34 | P2 | Phase 3: Formats | SP-PRS-10 | YAML document slicer | PRS | Extraction & Format Parsers | Planned | Low |  |  | SnakeYAML parser | Ingests Kubernetes and application YAML manifests
35 | P2 | Phase 3: Quality | SP-DQ-09 | Inline stream profiler & statistics | DQ | Data Quality, Validation & Cleansing | Partial | Med |  |  | DuckDB `SUMMARIZE` stream lowerer | Computes continuous null rates, min/max, distinct counts
36 | P2 | Phase 3: Quality | SP-DQ-08 | Fuzzy string (Jaro-Winkler) matcher | DQ | Data Quality, Validation & Cleansing | Planned | Low |  |  | DuckDB `jaro_winkler_similarity` | Entity matching and deduplication for spelling variations
37 | P2 | Phase 3: Quality | SP-DQ-07 | Cluster & edit value normalizer | DQ | Data Quality, Validation & Cleansing | Planned | Med |  |  | Fingerprint & ngram clustering | OpenRefine-style standardization for messy categorical data
38 | P2 | Phase 3: Quality | SP-DQ-10 | Statistical & reservoir sampler | DQ | Data Quality, Validation & Cleansing | Planned | Low |  |  | DuckDB `USING SAMPLE` lowerer | Extracts representative samples for testing and ML models
39 | P2 | Phase 3: Quality | SP-DQ-13 | One-way salted cryptographic hasher | DQ | Data Quality, Validation & Cleansing | Planned | Low |  |  | Function catalog `sha256(val, salt)` | Salted hashing for pseudonymizing identifier columns
40 | P2 | Phase 3: Transforms | SP-XFM-14 | DML row-action strategy flagger | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | Primary key diff logic (`__op=I/U/D`) | Flags changes for downstream target upsert/merge sinks
41 | P2 | Phase 3: Transforms | SP-XFM-15 | Dataset differ & change compare | XFM | Transformers & Dimensional Modeling | Partial | Med |  |  | Wrap `recon.run` into transform step | Emits diff delta records between two dataset snapshots
42 | P2 | Phase 3: Analytics | SP-BI-03 | Time-grain resampler & gap imputer | BI | Analytics, Time-Series & Semantic Modeling | Partial | Med |  |  | DuckDB `time_bucket()` + series filler | Normalizes irregular timeseries and imputes missing gaps
43 | P2 | Phase 3: Analytics | SP-BI-04 | Period-over-period shift | BI | Analytics, Time-Series & Semantic Modeling | Planned | Low |  |  | DuckDB `LAG() OVER (ORDER BY ts)` | Calculates YoY, MoM, WoW trends and growth rates
44 | P2 | Phase 3: Analytics | SP-BI-05 | Running calculations & moving avg | BI | Analytics, Time-Series & Semantic Modeling | Planned | Low |  |  | Window frame presets (`AVG() OVER`) | Computes rolling 7-day, 30-day averages and cumulative totals
45 | P2 | Phase 3: Analytics | SP-BI-07 | Semantic KPI calculator & metrics | BI | Analytics, Time-Series & Semantic Modeling | Partial | Med |  |  | Reusable KPI schema repository | Centralized business metric catalog reused across pipelines
46 | P2 | Phase 3: Analytics | SP-BI-08 | Template & runtime param injector | BI | Analytics, Time-Series & Semantic Modeling | Partial | Med |  |  | Jtwig / Pebble Jinja templating | Dynamic query templating with conditionals and loops
47 | P2 | Phase 3: Analytics | SP-BI-09 | Histogram & quantile binner | BI | Analytics, Time-Series & Semantic Modeling | Planned | Low |  |  | DuckDB `WIDTH_BUCKET()` / `NTILE()` | Segments continuous figures into buckets/deciles
48 | P2 | Phase 3: Geospatial | SP-BI-11 | H3 hexagonal grid indexer | BI | Analytics, Time-Series & Semantic Modeling | Planned | Med |  |  | DuckDB `h3` native extension | Geospatial spatial indexing for rideshare, IoT, logistics
49 | P2 | Phase 3: Geospatial | SP-BI-12 | Spatial polygon & point intersect | BI | Analytics, Time-Series & Semantic Modeling | Planned | Med |  |  | DuckDB `spatial` native extension | Boundary geofencing and spatial point-in-polygon joins
50 | P2 | Phase 3: Enrichment | SP-ENR-02 | GeoIP & ISP geolocation enricher | ENR | Enrichment, Entity Resolution & AI/ML | Planned | Low |  |  | MaxMind GeoIP2 Java reader | Translates client IP addresses to geographic coordinates
51 | P2 | Phase 3: Governance | SP-CTL-08 | SLA timeout & heartbeat monitor | CTL | Control, Governance & Sequence Integrity | Partial | Med |  |  | SLA declarative contract checker | Raises alarms when upstream data feeds miss delivery SLAs
52 | P2 | Phase 3: Destinations | SP-SNK-09 | ClickHouse / StarRocks analytical sink | SNK | Sinks, Storage & Destinations | Planned | Med |  |  | ClickHouse HTTP / JDBC bulk writer | High-throughput delivery into real-time OLAP databases
53 | P2 | Phase 3: Destinations | SP-SNK-10 | Excel multi-tab report sink | SNK | Sinks, Storage & Destinations | Planned | Med |  |  | FastExcel / POI workbook builder | Generates business-ready Excel sheets with totals
54 | P2 | Phase 3: Streaming | SP-ACQ-14 | Change Data Capture (Debezium) | ACQ | Collectors & Ingestion | Planned | High |  |  | Debezium message envelope parser | Ingests database changelogs for real-time replication
55 | P3 | Phase 4: Specialized | SP-ACQ-12 | RabbitMQ AMQP subscriber | ACQ | Collectors & Ingestion | Planned | Med |  |  | RabbitMQ client, acknowledgment queue | Ingests messages from enterprise RabbitMQ clusters
56 | P3 | Phase 4: Specialized | SP-ACQ-11 | AWS Kinesis / SQS ingest | ACQ | Collectors & Ingestion | Planned | Med |  |  | Kinesis Client Library (KCL) | Direct ingestion from AWS managed event streams
57 | P3 | Phase 4: Specialized | SP-ACQ-10 | Apache Pulsar consumer | ACQ | Collectors & Ingestion | Planned | Med |  |  | Apache Pulsar client | Enterprise multi-tenant streaming message consumption
58 | P3 | Phase 4: Specialized | SP-ACQ-13 | MQTT IoT telemetry ingest | ACQ | Collectors & Ingestion | Planned | Med |  |  | Eclipse Paho MQTT client | Lightweight sensor and edge device telemetry intake
59 | P3 | Phase 4: Specialized | SP-ACQ-20 | gRPC stream receiver | ACQ | Collectors & Ingestion | Planned | High |  |  | Netty gRPC server service handler | Ultra-high performance streaming binary RPC ingestion
60 | P3 | Phase 4: Telecom/Niche | SP-PRS-11 | ASN.1 PER / XER / DER decoder | PRS | Extraction & Format Parsers | Planned | High |  |  | `asn-parser` PER bytecode engine | Specialized telecom network protocol decoding
61 | P3 | Phase 4: Legacy | SP-PRS-12 | Mainframe EBCDIC & COBOL copybook | PRS | Extraction & Format Parsers | Planned | High |  |  | `JRecord` COBOL copybook parser | Decodes legacy banking and insurance mainframe files
62 | P3 | Phase 4: Cybersecurity | SP-PRS-15 | PCAP network packet slicer | PRS | Extraction & Format Parsers | Planned | High |  |  | Java NIO PCAP packet dissector | Packet inspection and network cybersecurity analysis
63 | P3 | Phase 4: Legacy | SP-DQ-11 | Character map & code page transcoder | DQ | Data Quality, Validation & Cleansing | Planned | Low |  |  | Java `Charset` transcoding stream | Handles legacy character sets (Shift-JIS, Windows-1252)
64 | P3 | Phase 4: Optimization | SP-XFM-11 | Presorted stream merge joiner | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | Two-way sorted stream iterator | Low-memory joins over pre-ordered multi-terabyte feeds
65 | P3 | Phase 4: Export | SP-XFM-16 | Hierarchical XML / JSON builder | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | StAX XML / Jackson struct serializer | Assembles relational rows into nested documents
66 | P3 | Phase 4: Vertical | SP-XFM-17 | IFRS 15 / IFRS 9 revenue engine | XFM | Transformers & Dimensional Modeling | Planned | High |  |  | Financial amortization macro | Automated financial accounting revenue recognition
67 | P3 | Phase 4: Vertical | SP-XFM-18 | SIM box & bypass fraud detector | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | CDR heuristics rule templates | Telecom bypass and unauthorized carrier routing fraud
68 | P3 | Phase 4: Vertical | SP-XFM-19 | Tariff, rating & usage billing | XFM | Transformers & Dimensional Modeling | Planned | High |  |  | Multi-dimensional rating matrix | Telco/utility usage rating and charge calculation
69 | P3 | Phase 4: Vertical | SP-XFM-20 | Roaming TAP3 / CIBER surcharger | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | TAP3 currency / fee calculator | Clearinghouse wholesale roaming billing
70 | P3 | Phase 4: Cybersecurity | SP-XFM-21 | Velocity & impossible travel anomaly | XFM | Transformers & Dimensional Modeling | Planned | Med |  |  | Haversine distance over time delta | Card transaction and login geolocation fraud detection
71 | P3 | Phase 4: BI | SP-BI-01 | LOD fixed aggregator | BI | Analytics, Time-Series & Semantic Modeling | Planned | Med |  |  | Window partition subquery compiler | Tableau-style independent grain aggregations
72 | P3 | Phase 4: BI | SP-BI-02 | LOD include / exclude aggregator | BI | Analytics, Time-Series & Semantic Modeling | Planned | Med |  |  | Contextual aggregation modifier | Dynamic inclusion/exclusion of group dimensions
73 | P3 | Phase 4: Analytics | SP-BI-06 | Time-series forecaster (Holt-Winters) | BI | Analytics, Time-Series & Semantic Modeling | Planned | High |  |  | Triple exponential smoothing math | Predictive baseline forecasting and capacity projection
74 | P3 | Phase 4: Transforms | SP-BI-10 | Smart custom string splitter | BI | Analytics, Time-Series & Semantic Modeling | Planned | Low |  |  | DuckDB `string_split_regex` | Complex delimiter splitting with quote tolerance
75 | P3 | Phase 4: Analytics | SP-BI-13 | Outlier detector & IQR boxplot fencer | BI | Analytics, Time-Series & Semantic Modeling | Planned | Low |  |  | DuckDB `percentile_cont()` | Statistical data cleaning and spike detection
76 | P3 | Phase 4: Analytics | SP-BI-14 | Correlation matrix (Pearson/Spearman) | BI | Analytics, Time-Series & Semantic Modeling | Planned | Low |  |  | DuckDB `CORR()` matrix query | Feature selection and multi-variable correlation
77 | P3 | Phase 4: Legacy | SP-ENR-05 | Parameterized stored-procedure caller | ENR | Enrichment, Entity Resolution & AI/ML | Planned | Med |  |  | JDBC `CallableStatement` runner | Executes complex legacy RDBMS stored procedures
78 | P3 | Phase 4: Advanced MDM | SP-ENR-06 | Master entity resolution & linkage | ENR | Enrichment, Entity Resolution & AI/ML | Planned | High |  |  | Fellegi-Sunter probabilistic matcher | Enterprise single-customer view record linkage
79 | P3 | Phase 4: Advanced MDM | SP-ENR-07 | Graph cluster & component tagger | ENR | Enrichment, Entity Resolution & AI/ML | Partial | Med |  |  | Graph connected-component worker | Fraud syndicate and account linkage graph tagging
80 | P3 | Phase 4: AI/ML | SP-ENR-08 | ONNX Runtime embedded inference | ENR | Enrichment, Entity Resolution & AI/ML | Planned | High |  |  | `inspecto-intelligence` onnxruntime | Low-latency in-process ML model scoring
81 | P3 | Phase 4: AI/ML | SP-ENR-09 | LLM zero-shot classifier & tagging | ENR | Enrichment, Entity Resolution & AI/ML | Planned | Med |  |  | Gemini / OpenAI API batch client | Unstructured text tagging and intent classification
82 | P3 | Phase 4: AI/ML | SP-ENR-10 | Text embeddings & vector generator | ENR | Enrichment, Entity Resolution & AI/ML | Planned | Med |  |  | Text embedding model integration | Generates vector arrays for semantic similarity
83 | P3 | Phase 4: Cloud Output | SP-SNK-12 | AWS SQS / SNS event publisher | SNK | Sinks, Storage & Destinations | Planned | Med |  |  | AWS SDK v2 SQS/SNS client | Emits batch arrival events to AWS event consumers
84 | N/A | Maintain Internal | SP-CTL-06 | Transaction & commit controller | CTL | Control, Governance & Sequence Integrity | Partial | Low |  |  | *Already internal to engine* | Handled transparently by `BranchCommitCoordinator`
85 | N/A | Maintain Legacy | SP-SNK-04 | Derived view | SNK | Sinks, Storage & Destinations | Partial | Low |  |  | *Superseded by Datasets/Views* | Grandfathered type maintained for backwards compatibility

## All 119 Processors
Board ID | Catalog ID | Emoji | Processor Label | Family Code | Family Name | Status | Maps To | Capability / Seam | Addable in UI | Notes & Gaps
SP-ACQ-01 | acquisition.file.local | 📁 | Local / NFS directory watcher | ACQ | Collectors & Ingestion | Delivered | acquisition | — | Yes | LocalFileSystemConnector — the default collector
SP-ACQ-02 | acquisition.file.sftp | 🔒 | SFTP / FTPS remote ingest | ACQ | Collectors & Ingestion | Delivered | acquisition | — | Yes | inspecto-connectors (sftp, ftps; key auth, bastion tunnel, host-key pinning)
SP-ACQ-03 | acquisition.db.jdbc | 🗄️ | JDBC / SQL query batch reader | ACQ | Collectors & Ingestion | Delivered | acquisition | — | Yes | the db-export connector (`connector: db`, watermark column)
SP-ACQ-04 | acquisition.dataset | 🧱 | Dataset entry (re-ingest a registered Dataset) | ACQ | Collectors & Ingestion | Delivered | acquisition | — | Yes | UI-S7: `connector: dataset` + `on:dataset` trigger
SP-ACQ-05 | acquisition.file.excel | 📑 | Multi-sheet Excel workbook ingest | ACQ | Collectors & Ingestion | Partial | parser.xlsx | — | Yes | the xlsx PARSER is delivered; per-sheet workbook fan-out as an acquisition is not
SP-ACQ-06 | acquisition.file.s3 | ☁️ | AWS S3 object ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-07 | acquisition.file.azure | 🌐 | Azure Blob & ADLS Gen2 ingest | ACQ | Collectors & Ingestion | Partial | acquisition | — | Yes | Connection kind exists (azure blob connector); ADLS Gen2 semantics not proven
SP-ACQ-08 | acquisition.file.gcs | 🪣 | Google Cloud Storage ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-09 | acquisition.stream.kafka | 📤 | Apache Kafka consumer | ACQ | Collectors & Ingestion | Partial | acquisition | — | Yes | Connection kind exists (kafka); consumer-group ingest as a Collector not proven
SP-ACQ-10 | acquisition.stream.pulsar | 📨 | Apache Pulsar consumer | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-11 | acquisition.stream.kinesis | 📬 | AWS Kinesis / SQS ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-12 | acquisition.stream.rabbitmq | 🐰 | RabbitMQ AMQP subscriber | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-13 | acquisition.stream.mqtt | 📡 | MQTT IoT telemetry ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-14 | acquisition.cdc.debezium | 🔄 | Change Data Capture (Debezium) | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-15 | acquisition.lake.delta | 💾 | Delta Lake table reader | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-16 | acquisition.lake.iceberg | 🧊 | Apache Iceberg table ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-17 | acquisition.db.cloud | ❄️ | Snowflake / BigQuery ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-18 | acquisition.api.rest | 🌐 | REST API poller & paged ingest | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-19 | acquisition.api.webhook | 🪝 | HTTP webhook listener endpoint | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-ACQ-20 | acquisition.api.grpc | 🔌 | gRPC stream receiver | ACQ | Collectors & Ingestion | Planned | — | — | No
SP-PRS-01 | parser.delimited | 📄 | Delimited / CSV / TSV / PSV parser | PRS | Extraction & Format Parsers | Delivered | parser.delimited | — | Yes
SP-PRS-02 | parser.fixedwidth | 📦 | Fixed-width column slicer | PRS | Extraction & Format Parsers | Delivered | parser.fixedwidth | — | Yes | text (`record: line`) and fixed-length binary (`record: bytes`)
SP-PRS-03 | parser.json | 🧬 | JSON object & JSON Lines (NDJSON) parser | PRS | Extraction & Format Parsers | Delivered | parser.json | — | Yes
SP-PRS-04 | parser.excel | 📑 | Excel workbook parser | PRS | Extraction & Format Parsers | Delivered | parser.xlsx | — | Yes | needs the DuckDB `excel` extension in the bundle (multiformat X1)
SP-PRS-05 | parser.xml | 📑 | XML / XPath / DOM unpacker | PRS | Extraction & Format Parsers | Partial | parser.plugin | — | Yes | tree→segments bridge ships XML ingests; no XPath selector grammar yet
SP-PRS-06 | parser.asn1.ber | 📡 | ASN.1 BER telecom CDR decoder | PRS | Extraction & Format Parsers | Delivered | — | parser.asn1 | No | asn-parser reactor (decoders, vendor plugins)
SP-PRS-07 | parser.pattern.regex | 🔎 | Named-group regex extractor | PRS | Extraction & Format Parsers | Delivered | parser.text_regex | — | Yes
SP-PRS-08 | parser.plugin | 🧩 | Custom ingester plugin (segments, multi-event) | PRS | Extraction & Format Parsers | Delivered | parser.plugin | — | Yes | ParserPlugin SPI; `segments: {CALL, SMS}`
SP-PRS-09 | parser.keyvalue | 🏷️ | Key-value / logfmt parser | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-10 | parser.yaml | 📜 | YAML document slicer | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-11 | parser.asn1.per | 📜 | ASN.1 PER / XER / DER decoder | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-12 | parser.mainframe.ebcdic | 📠 | Mainframe EBCDIC & COBOL copybook | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-13 | parser.binary.protobuf | ⚡ | Protocol Buffers decoder | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-14 | parser.binary.avro | 🦅 | Apache Avro binary decoder | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-15 | parser.binary.pcap | 🌐 | PCAP network packet slicer | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-16 | parser.pattern.grok | 📜 | Grok / Logstash expression matcher | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-PRS-17 | parser.pattern.syslog | 🖥️ | Syslog RFC 5424 / RFC 3164 parser | PRS | Extraction & Format Parsers | Planned | — | — | No
SP-DQ-01 | quality.schema.validator | 🛡️ | Schema registry & structural rejects | DQ | Data Quality, Validation & Cleansing | Delivered | parser | — | No | the declared schema on the Parse Step: typed fields, TRY_CAST at ingest, structural rejects → quarantine. ⛔ Only HALF of the old "Schema validator & type coercion" — coercion as an AUTHORING act folded into `transform.record` (2026-09-04). What cannot fold is the schema CONTRACT: the declared source column + target type are the cast-failure audit's denominator, and `SchemaCompatibility` gates edits to them BACKWARD
SP-DQ-02 | quality.constraint.check | ⚠️ | Constraint & range checker (Expectations) | DQ | Data Quality, Validation & Cleansing | Delivered | — | expectation | No | Expectations evaluated per Dataset (`ExpectationEvaluator`); not a mid-chain step
SP-DQ-03 | quality.dedup.exact | 🧼 | Exact-key deduplicator (within a Consignment) | DQ | Data Quality, Validation & Cleansing | Delivered | transform.dedup | — | Yes | `scope: consignment` (default)
SP-DQ-04 | quality.dedup.windowed | ⏱️ | Sliding time-window deduplicator | DQ | Data Quality, Validation & Cleansing | Delivered | transform.dedup | — | Yes | D-9: `scope: window(P4D)` + the durable dedup ledger
SP-DQ-05 | quality.dedup.file | 🗂️ | File-grain duplicate guard (path / checksum / metadata / marker) | DQ | Data Quality, Validation & Cleansing | Delivered | acquisition | — | Yes | Collector `duplicate:` policy + marker dedup — a Guarantee, rides the Collector
SP-DQ-06 | quality.schema.drift | 🧬 | Schema drift & new-field detector | DQ | Data Quality, Validation & Cleansing | Partial | — | expectation | No | multi-schema dispatch refuses unknown shapes; no drift REPORT yet
SP-DQ-07 | quality.cluster.edit | 🔍 | Cluster & edit value normalizer | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No
SP-DQ-08 | quality.match.fuzzy | 🔍 | Fuzzy string (Jaro-Winkler) matcher | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No
SP-DQ-09 | quality.profiler.inline | 🧮 | Inline stream profiler & statistics | DQ | Data Quality, Validation & Cleansing | Partial | — | storage_report | No | storage/completeness KPIs exist; no per-column profile step
SP-DQ-10 | quality.sample.reservoir | 📊 | Statistical & reservoir sampler | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No
SP-DQ-11 | quality.cleanse.transcode | 🔤 | Character map & code page transcoder | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No
SP-DQ-12 | quality.pii.mask | 🔒 | PII masking & tokenization | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No | board SEC-08 — Enterprise only
SP-DQ-13 | quality.crypto.hash | 🔑 | One-way salted cryptographic hasher | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No
SP-DQ-14 | quality.compliance.redact | 🛡️ | GDPR / CCPA field redactor | DQ | Data Quality, Validation & Cleansing | Planned | — | — | No | board SEC-08 — Enterprise only
SP-XFM-01 | transform.record | 🧮 | Record Transformer | XFM | Transformers & Dimensional Modeling | Delivered | transform.sql | — | Yes | ONE Step that shapes a record: sanitize (trim/pad/replace/case), cast, rename and computed columns — one row per output field over a typed function catalog, generating the SELECT it saves. Folded 2026-09-04 from `transform.expression` + `transform.cast` + `quality.cleanse.trim`, which were three catalog labels over this one grid. `transform.map` was deleted 2026-09-05: a stored `mapping.rules[]` is read as `fields[]` (EXPR → custom, CONCAT_DT → date.concat_parts, FILENAME_DATE → date.from_filename)
SP-XFM-02 | transform.filter | 🔽 | Row filter (pre-parse regex / post-map predicate) | XFM | Transformers & Dimensional Modeling | Delivered | transform.filter | — | Yes
SP-XFM-03 | transform.route | 🔀 | Router — case / clone branches with mid-branch steps | XFM | Transformers & Dimensional Modeling | Delivered | transform.route | — | Yes
SP-XFM-04 | transform.summarize | ∑ | Group-by summarizer (measures grammar) | XFM | Transformers & Dimensional Modeling | Delivered | transform.summarize | — | Yes
SP-XFM-05 | transform.join | 🤝 | Reference-store join (versioned references) | XFM | Transformers & Dimensional Modeling | Delivered | transform.join | — | Yes | at rest only — refused mid-branch (no reference resolver on the ingest lane)
SP-XFM-06 | transform.lookup | 🗺️ | Lookup & static map transcoder | XFM | Transformers & Dimensional Modeling | Delivered | transform.lookup | — | Yes | inline key=value map over one column (2026-09-06); a versioned reference is transform.join
SP-XFM-07 | transform.matrix.pivot | 🔀 | Dynamic pivot / transpose | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-08 | transform.matrix.unpivot | 🔄 | Unpivot / column flattener | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-09 | transform.analytics.rank | 🏆 | Rank & Top-N pruner | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-10 | transform.explode | 💥 | Array / object exploder & flattener | XFM | Transformers & Dimensional Modeling | Planned | — | — | No | the grandfathered `transform.split` node type is the read-only ancestor
SP-XFM-11 | transform.join.merge | 🤝 | Presorted stream merge joiner | XFM | Transformers & Dimensional Modeling | Planned | — | — | No | the grandfathered `transform.merge` node type is the read-only ancestor
SP-XFM-12 | transform.dim.scd2 | 🏛️ | Slowly changing dimension (SCD Type 2) | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-13 | transform.key.surrogate | 🔑 | Monotonic surrogate key generator | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-14 | transform.dml.strategy | 🏷️ | DML row-action strategy flagger | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-15 | transform.diff.compare | ⚖️ | Dataset differ & change compare | XFM | Transformers & Dimensional Modeling | Partial | — | recon | No | Reconciliation boards compare Datasets; not a chain step
SP-XFM-16 | transform.builder.xml | 🏗️ | Hierarchical XML / JSON document builder | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-17 | transform.fintech.ifrs | 📊 | IFRS 15 / IFRS 9 revenue recognition engine | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-18 | transform.telecom.simbox | 📱 | SIM box & bypass fraud detector | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-19 | transform.telecom.rating | 💵 | Tariff, rating & usage billing engine | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-20 | transform.telecom.roaming | 🌍 | Roaming TAP3 / CIBER surcharger | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-XFM-21 | transform.fintech.velocity | 🚨 | Velocity & impossible-travel anomaly | XFM | Transformers & Dimensional Modeling | Planned | — | — | No
SP-BI-01 | transform.analytics.lod | 🏛️ | Level-of-detail (LOD) fixed aggregator | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-02 | transform.analytics.lod_context | 🏛️ | LOD include / exclude context aggregator | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-03 | transform.timeseries.resample | ⏱️ | Time-grain resampler & gap imputer | BI | Analytics, Time-Series & Semantic Modeling | Partial | — | measure-grammar | No | time grains exist in Studio queries (`QuerySpec.grains`); no resampling step
SP-BI-04 | transform.timeseries.shift | 📈 | Period-over-period (YoY / MoM / WoW) shift | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-05 | transform.analytics.running | 📊 | Running calculations & moving averages | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-06 | transform.timeseries.forecast | 🔮 | Time-series forecaster (Holt-Winters) | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-07 | transform.semantic.metric | 📐 | Semantic KPI calculator & Measure formulas | BI | Analytics, Time-Series & Semantic Modeling | Partial | — | measure-grammar | No | the Measure grammar (`count ¦ agg(field)`) serves Studio + summarize; no named-KPI layer
SP-BI-08 | transform.param.jinja | 🏷️ | Template & runtime parameter injector | BI | Analytics, Time-Series & Semantic Modeling | Partial | — | sql.template | No | the `sql.template` job resolves `$name` tokens; no Jinja
SP-BI-09 | transform.data.binning | 📦 | Histogram & quantile binner | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-10 | transform.string.smart_split | ✂️ | Smart custom string splitter | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-11 | transform.geo.h3 | 🗺️ | H3 hexagonal & geohash grid indexer | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No | needs the DuckDB `spatial`/`h3` extension — board CP-09 gate
SP-BI-12 | transform.geo.spatial_join | 📍 | Spatial polygon & point-in-polygon intersect | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No | needs the DuckDB `spatial` extension — deliberately not loaded (SqlSandbox)
SP-BI-13 | transform.stats.outlier | 🚨 | Outlier detector & IQR boxplot fencer | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-BI-14 | transform.stats.correlation | 🧮 | Pearson & Spearman correlation matrix | BI | Analytics, Time-Series & Semantic Modeling | Planned | — | — | No
SP-ENR-01 | enrichment.reference | 📚 | Reference-table enrichment (`*_enrich.toon`, Stage-2) | ENR | Enrichment, Entity Resolution & AI/ML | Delivered | enrichment | — | Yes | the shipped enrichment job + versioned references
SP-ENR-02 | enrichment.geoip | 🌍 | GeoIP & ISP geolocation enricher | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No
SP-ENR-03 | enrichment.redis | ⚡ | Redis / in-memory cache lookup | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No
SP-ENR-04 | enrichment.rest | 🌐 | Dynamic microservice REST enricher | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No
SP-ENR-05 | transform.db.procedure | 🗄️ | Parameterized stored-procedure caller | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No
SP-ENR-06 | enrichment.entity.link | 🔗 | Master entity resolution & record linkage | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No
SP-ENR-07 | enrichment.graph.cluster | 🕸️ | Graph cluster & connected-component tagger | ENR | Enrichment, Entity Resolution & AI/ML | Partial | — | link-analysis | No | link-analysis VIEW ships (projection); no tagging step
SP-ENR-08 | ml.inference.onnx | 🤖 | ONNX Runtime embedded inference | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No | the optional `inspecto-intelligence` module carries onnxruntime; never bundled
SP-ENR-09 | ml.llm.classify | 🏷️ | LLM zero-shot classifier & tagging | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No | assist/intelligence agents are never bundled (CP-14)
SP-ENR-10 | ml.embedding.vector | 📐 | Text embeddings & vector generator | ENR | Enrichment, Entity Resolution & AI/ML | Planned | — | — | No
SP-CTL-01 | control.file.sequence_analyzer | 🕳️ | File sequence & gap integrity analyzer | CTL | Control, Governance & Sequence Integrity | Delivered | gap | — | Yes | Collector `gap_detection: {sequence}` → the gap node + SEQUENCE_GAP events
SP-CTL-02 | control.gap.detector | 🕳️ | Sequence-gap & data-loss watchdog | CTL | Control, Governance & Sequence Integrity | Delivered | gap | — | Yes | same detector; gaps raise ALERT objects via the EventObjectBridge
SP-CTL-03 | control.audit.stamp | 🏷️ | Audit metadata & lineage stamper | CTL | Control, Governance & Sequence Integrity | Delivered | sink.persistent | — | Yes | `filename_column` + the per-file/batch/lineage ledgers + `__batch_id` provenance
SP-CTL-04 | control.throttle | ⏳ | Throttle & rate limiter | CTL | Control, Governance & Sequence Integrity | Delivered | acquisition | — | Yes | Collector `fetch.rate_limit` + intake caps + the concurrency broker
SP-CTL-05 | control.circuitbreaker | 🚦 | Circuit breaker & fallback switch | CTL | Control, Governance & Sequence Integrity | Delivered | acquisition | — | Yes | Collector `circuit_breaker` + `retry`
SP-CTL-06 | control.transaction.commit | 🏁 | Transaction & commit controller | CTL | Control, Governance & Sequence Integrity | Partial | — | engine | No | the BranchCommitCoordinator ledger + bounded COMMIT retry are engine-internal, not authorable
SP-CTL-07 | control.alert.dispatch | 🚨 | Alert rule dispatcher | CTL | Control, Governance & Sequence Integrity | Delivered | — | alert-rule | No | Alert Rules over the ledgers → Alerts → channels; board CP-11/CP-15
SP-CTL-08 | control.sla.monitor | ⏱️ | SLA timeout & heartbeat monitor | CTL | Control, Governance & Sequence Integrity | Partial | — | completeness-kpi | No | completeness KPI + `heartbeat` maintenance task; no SLA object
SP-SNK-01 | sink.file.parquet | 📁 | Parquet (snappy / zstd / gzip) partitioned store | SNK | Sinks, Storage & Destinations | Delivered | sink.persistent | — | Yes | Hive `year=/month=/day=` partitions
SP-SNK-02 | sink.file.csv | 📄 | CSV partitioned store | SNK | Sinks, Storage & Destinations | Delivered | sink.persistent | — | Yes | `output.format: CSV`
SP-SNK-03 | sink.ducklake | 🦆 | DuckLake catalog (PostgreSQL) sink | SNK | Sinks, Storage & Destinations | Delivered | sink.persistent | — | Yes | `output.ducklake` — needs the postgresql sidecar (Standard+)
SP-SNK-04 | sink.view | 👁️ | Derived view (no bytes, registered SQL) | SNK | Sinks, Storage & Destinations | Partial | sink.view | — | No | grandfathered node type; the Dataset/View surface replaced it
SP-SNK-05 | sink.quarantine | ☣️ | Quarantine error-log store | SNK | Sinks, Storage & Destinations | Delivered | — | sink.quarantine | No | structural rejects + `errors/<base>_errors.csv`
SP-SNK-06 | sink.archive | 📜 | Long-term compliance archive | SNK | Sinks, Storage & Destinations | Delivered | acquisition | — | Yes | Collector `post_action: MOVE archive_path` + the `backup` maintenance task
SP-SNK-07 | sink.lake.delta | 🗄️ | Delta Lake persistent table sink | SNK | Sinks, Storage & Destinations | Planned | — | — | No
SP-SNK-08 | sink.lake.iceberg | 🧊 | Apache Iceberg append / upsert sink | SNK | Sinks, Storage & Destinations | Planned | — | — | No
SP-SNK-09 | sink.db.clickhouse | 📊 | ClickHouse / StarRocks analytical sink | SNK | Sinks, Storage & Destinations | Planned | — | — | No
SP-SNK-10 | sink.file.excel | 📑 | Excel multi-tab report sink | SNK | Sinks, Storage & Destinations | Planned | — | — | No
SP-SNK-11 | sink.stream.kafka | 📤 | Apache Kafka topic producer | SNK | Sinks, Storage & Destinations | Planned | — | — | No
SP-SNK-12 | sink.stream.aws | 📨 | AWS SQS / SNS event publisher | SNK | Sinks, Storage & Destinations | Planned | — | — | No
SP-SNK-13 | sink.notify.email | 📧 | Email & report dispatcher | SNK | Sinks, Storage & Destinations | Partial | — | mail.send | No | the `mail.send` JOB + mail channels; not a chain sink
SP-SNK-14 | sink.api.webhook | 🪝 | Outbound webhook dispatcher | SNK | Sinks, Storage & Destinations | Partial | — | channel | No | webhook notification channel exists; not a chain sink
SP-SNK-15 | sink.dlq | 🕳️ | Dead-letter queue | SNK | Sinks, Storage & Destinations | Planned | — | — | No

## Dashboard & KPIs
Inspecto Step Processors Portfolio Dashboard
Portfolio Status Summary (All 119 Processors)
Family Code | Family Label | Delivered (✅) | Partial (🟡) | Planned (🔲) | Total Processors | % Delivered
ACQ | Collectors & Ingestion
PRS | Extraction & Format Parsers
DQ | Data Quality, Validation & Cleansing
XFM | Transformers & Dimensional Modeling
BI | Analytics, Time-Series & Semantic Modeling
ENR | Enrichment, Entity Resolution & AI/ML
CTL | Control, Governance & Sequence Integrity
SNK | Sinks, Storage & Destinations
TOTAL | All 8 Families
Pending Processors Priority Distribution (Sheet: Priority & Sequence)
Priority Tier | Definition | Count | % of Pending Backlog
P0 | Critical / Immediate (Phase 1 Baseline & Quick Wins)
P1 | High Value (Lakehouse, Streaming, Modeling, Security)
P2 | Medium Value (Multi-Cloud, Advanced Analytics, Quality)
P3 | Specialized / Niche (Telecom, FinTech, Legacy, AI/ML)
N/A | Internal Engine Core or Superseded Capabilities
TOTAL | Total Pending Backlog |  | 100.0%